## PROJECT
PROJECT TITLE: |  | ONLINE TOBACCO AUCTION SYSTEM FOR REGION COOPERATIVE UNION
MAIN OBJECTIVE: |  | TO DESIGN AND CREATE A SYSTEM WHICH SIMPLIFY THE BUSINESS/BID FOR TOBACCO PRODUCT
SPECIFIC OBJECTIVES: | 1 | Consultation with experienced personel in tobacco production and business in general to get requirements
(Depends on the number of your objectives) | 2 | To design database concerned with our system(E-R Diagrams)
| 3 | To create database(implementation of the designs)
| 4 | Designing of user interface
| 5 | Creating user interface
| 6 | Discussion of the backend logic
| 7 | Building up the backend logic and connecting the user interface with the database
| 8 | System testing
Identify the stakeholders in your project
| 1 | Customers
| 2 | Programmers
3
4
5
6
7
8
9
.
.
.
.

## DELIVERABLES
S/N. | GOAL/OBJECTIVE | DELIVERABLE(S) | Estimated Delivery Date
1 | Consultation with experienced personel in tobacco production and business in general | Meeting report
2 | To design database concerned with our system | E-R diagrams
3 | To create database | Prototype of the database design
4 | Designing of user interface | Design drawings
5 | Creating user interface | Prototype of User interface
6 | Discussion of the backend logic | Meeting report
7 | Building up the backend logic and connecting the user interface with the database | Finished System
8 | System testing | Finished Product(System)
9 | Deployment
10 | Maintanance
***You will establish more accurate delivery dates during the scheduling phase, which is next.

## SCHEDULE
S/N. | TASK | LEAD | EFFORT(hours or days or weeks)
1 | Speaking with experienced personel | Mabula Paul | 2days
2 | Database design | Tamba Paul | 5days
3 | Creating database | Tamba Paul | 5days
4 | Designing of the user interface | Juma Epaflas | 2days
5 | Creating user interface | Juma Epaflas | 5days
6 | Discussion of the backend logic | Gotifridi Lina | 2days
7 | Building backend and connecting with BD | Magaya John | 11days
8 | System testing | Magaya John | 2days
.
.
.
.
.
https://github.com/Paultamba/TOBACCO-AUCTION.git
This is a system for managing the auction conducted every year seasonally for the tobacco agricultural product

## GANTTCHART
[Project Name] Project Schedule | ONLINE TOBACCO AUCTION SYSTEM
[Company Name]
| Project Start Date | 2020-08-01 |  |  |  | Display Week | 1 |  | Week 1 | [6 empty] | Week 2 | [6 empty] | Week 3 | [6 empty] | Week 4 | [6 empty] | Week 5 | [6 empty] | Week 6 | [6 empty] | Week 7 | [6 empty] | Week 8
| Project Lead | [7 empty] | 2020-07-27 | [6 empty] | 2020-08-03 | [6 empty] | 2020-08-10 | [6 empty] | 2020-08-17 | [6 empty] | 2020-08-24 | [6 empty] | 2020-08-31 | [6 empty] | 2020-09-07 | [6 empty] | 2020-09-14
 | time axis 2020-07-27 to 2020-09-20
WBS | TASK | LEAD | PREDECESSOR | START | END | DAYS | % DONE | WORK DAYS | time axis 2020-07-27 to 2020-09-20
1 | [Task Category / Objective] |  |  |  | - |  |  | -
1.1 | [Speaking with experienced personel] | [Mabula Paul] |  | 2020-08-01 | 2020-08-02 | 2 | 100%
1.2 | [Database design] | Tamba Paul |  | 2020-08-03 | 2020-08-07 | 5 | 60%
1.3 | [Creating Database] | Tamba Paul |  | 2020-08-08 | 2020-08-12 | 5 | 0%
1.4 | [Designing User interface] | Juma, Epaflas |  | 2020-08-13 | 2020-08-14 | 2 | 75%
1.5 | [Creating user interface] | Masulende Epaflas |  | 2020-08-15 | 2020-08-19 | 5 | 0%
1.6 | [Discussion of backend logic] | Gotifrid Linah |  | 2020-08-20 | 2020-08-21 | 2 | 0%
1.7 | [Building backend and connecting with interface] | Magaya John |  | 2020-08-22 | 2020-09-04 | 14 | 0% | 10
1.8 | System Testing | Magaya John |  | 2020-09-05 | 2020-09-06 | 2 |  | 0
2 | [Task Category / Objective] |  |  |  | - |  |  | -
2.1 | [Task] |  |  | 2018-02-10 | 2018-02-13 | 4 | 0% | 2
2.2 | [Task] |  |  | 2018-02-14 | 2018-02-16 | 3 | 0% | 3
2.3 | [Task] |  |  | 2018-02-14 | 2018-02-16 | 3 | 0% | 3
2.4 | [Task] |  |  | 2018-02-17 | 2018-02-22 | 6 | 0% | 4
2.5 | [Task] |  |  | 2018-02-23 | 2018-02-25 | 3 | 0% | 1
3 | [Task Category / Objective] |  |  |  | - |  |  | -
3.1 | [Task] |  |  | 2018-02-10 | 2018-02-13 | 4 | 0% | 2
3.2 | [Task] |  |  | 2018-02-14 | 2018-02-16 | 3 | 0% | 3
3.3 | [Task] |  |  | 2018-02-14 | 2018-02-16 | 3 | 0% | 3
3.4 | [Task] |  |  | 2018-02-17 | 2018-02-22 | 6 | 0% | 4
3.5 | [Task] |  |  | 2018-02-23 | 2018-02-25 | 3 | 0% | 1
4 | [Task Category / Objective] |  |  |  | - |  |  | -
4.1 | [Task] |  |  | 2018-01-29 | 2018-01-29 | 1 | 0% | 1
4.2 | [Task] |  |  | 2018-01-30 | 2018-01-30 | 1 | 0% | 1
4.3 | [Task] |  |  | 2018-01-31 | 2018-01-31 | 1 | 0% | 1
4.4 | [Task] |  |  | 2018-02-01 | 2018-02-01 | 1 | 0% | 1
4.5 | [Task] |  |  | 2018-02-02 | 2018-02-02 | 1 | 0% | 1
-
-
TEMPLATE ROWS
See the Help worksheet to learn how to use these rows. You can hide these rows before printing.
1 | [ Level 1 Task or Phase ] |  |  |  | - |  |  | -
1.1 | . [ Level 2 Task ] |  |  |  | - |  |  | -
1.1.1 | . . [ Level 3 Task ] |  |  |  | - |  |  | -
1.1.1.1 | . . . [ Level 4 Task ] |  |  |  | - |  |  | -
► Watch How to Create a Gantt Chart in Excel
Note on A7: Work Breakdown Structure Level 1: 1, 2, 3, ... Level 2: 1.1, 1.2, 1.3, ... Level 3: 1.1.1, 1.1.2, 1.1.3, … - The WBS uses a formula to control the numbering, but the formulas are different for different levels. Copy and Paste the cells in the WBS column from the examples at the bottom of the worksheet.
Note on B7: Task Description Enter the name of each task and sub-task. Use indents for sub-tasks.
Note on C7: Task Lead Enter the name of the Task Lead in this column.
Note on D7: Predecessor Tasks: You can use this column to enter the WBS of a predecessor for reference. The PRO version uses formulas to automatically calculate the Start Date based on the Predecessor.
Note on E7: Task Start Date You can manually enter the Start Date for each task or use a formula to create a dependency on a Predecessor. For example, you could enter =enddate+1 to set the Start date to the next calendar day, or =WORKDAY(enddate,1) to set the Start date to the next work day (excluding weekends), where enddate is the cell reference for the End date of the Predecessor task.
Note on F7: End Date: The End Date is calculated based on the Start Date and the Calendar Days columns.
Note on G7: Duration (Calendar Days) The duration is the number of calendar days for the given task. The duration is calculated as the End Date minus the Start Date plus 1 day, so that a task starting and ending on the same day has a duration of 1 day. Note: The conditional formatting used to create the gantt chart references this column.
Note on H7: Percent Complete Update the status of this task by entering the percent complete (between 0% and 100%).
Note on I7: Work Days Counts the number of work days, excluding the weekends (Saturday and Sunday). In the PRO version, you can customize the work week and list specific non-working days like holidays. In the PRO version, the default input is the Work Days instead of the Calendar Days.

## CONSTRAINTS
S/N. | PROJECT CONSTRAINTS
1 | Cost(Purchasing of Database,and other resources)
2 | Time(The project will take not more than two months)
3 | Scope(The scope is Regionwise so somehow Bigger)
4 | Quality(Needs to be of great assuarance)
5 | Risks
.
.
.
***Project constraints are anything that restricts or dictates the actions of the project team.
https://pmtips.net/article/defining-project-constraints#:~:text=Project%20constraints%20are%20anything%20that,not%20all%20three%20project%20constraints.

## RISK MANAGEMENT
S/N. | RISK | WHAT WILL YOU DO IF IT HAPPENS |  | WHAT WILL YOU DO TO MITIGATE IT (PREVENT IT FROM HAPPENING)
1 | Denies for direct contact meeting due to the spreed of COVID-19 | 1 | Conducting video conference meeting or by Phone call | 1 | Convicing personnel to conduct a meeting with a care
|  | 2 | Sending a questionnaire (interview questions) by email | 2 | Provide protective gears to the members of the project
|  | 3 |  | 3
4
2 | Requirements inflation
|  | 1 | Provide a view to the customer to understand the impact of changes |  | Clear and carefully declaration of the requirements before system design
3 | Specification breakdown
|  | 1 | Reassign tasks to the members |  | Simplify as possible the requirements/specifications
4
5
6
7

## REQUIREMENTS
FUNCTIONAL REQUIREMENTS
1 | The system must allow regional administrators to manage the bids
2 | The system must allow all users to view details in accordance with their roles
3 | The system must record regional centres information
4 | The system must require aunthentication information from each user
NON FUNCTIONAL REQUIREMENTS
1 | The system should allow only three administrators
2 | The username in aunthentication details should be an email address
3 | The system should have backup after every bid
4 | The system shoukd run in all platforms
5 | The System must be web based system

## GROUP MEMBERS
NAME OF THE MEMBER | REG NO.
TAMBA, PAUL JOHN | 2018-04-02524
MABULA,PAUL R | 2018-04-02525
GOTIFRIDI,LINA LADISLAUS | 2018-04-02518
MAGAYA, JOHN | 2018-04-13191
JUMA,EPAFLAS | 2018-04-07817